## Unified WBS
DIS — Unified Work Breakdown Structure (WBS) — Consolidated Single Sheet
Risk levels: GREEN = completed/on track ¦ YELLOW = pending/monitoring/future planned ¦ RED = dependency/attention required. Risk Level cells use conditional formatting and update when GREEN, YELLOW, or RED is typed.
LEGEND: | YELLOW — Pending / Monitor | RED — Attention Required | GREEN — Completed / On Track
# | Source / Workstream | Work Item | Sub-Task | Jira Ref | Owner | Status | Start Date | Target / End Date | Dependencies | Blockers / Risk | Risk Level | Deloitte Comment | OV Comment
0. Assumptions
1 | Assumptions | A1 — Next sprint activity dates are dependent on rebuild phase completion. | [9 empty] | PM / Delivery Lead to publish detailed dates after rebuild sign-off.
2 | Assumptions | A2 — Rebuild completion is the gating dependency for staging and production planning. | [9 empty] | Track rebuild blockers daily and re-plan downstream activities if needed.
3 | Assumptions | A3 — Required environment access, IAM/GCP permissions, CI/CD access, secrets, test data, and provider/mock availability will be available before execution. | [9 empty] | Owners to raise access or readiness blockers immediately.
4 | Assumptions | A4 — Dates have been removed from the Rebuild plan due to dependencies on Doc Processor portability, an update on this will be given on Thursday/Friday. Planned dates and updated activities for Staging & Prod will be added after the Rebuild is completed. Learnings from the Rebuild phase will be incorporated into the Staging & Prod planning. | [9 empty] | The whole rebuild plan will take 8 working days to complete. This is an add-on request being taken up by the team to further check the robustness and ensure learnings are applied before Staging & Prod planning is finalized.
5 | Assumptions | A5 — Scope focus will remain on the deliverables listed in this WBS; any new changes or additional requests can be added in the next sprint. | [9 empty] | This controls scope for the current plan and allows new requests to be assessed, prioritized, and planned through the next sprint backlog.
6 | Assumptions | A6 — Datadog integration is not planned for this sprint, as the team is prioritizing closure of the current deliverables. After these are completed, the team can review the Confluence document and share relevant comments.
7 | Assumptions | A7 — An E2E run is targeted to be available for Chris to perform by 29th - 30th June, based on the API specifications discussed and approved during SCRUM 17. The updated API specifications are not considered for this E2E run.
1. Relevant Links
6 | Integration Test Pipeline | https://openvisa.atlassian.net/wiki/spaces/DD/pages/123469825/DIS+Integration+Testing+Pipeline+Overview
7 | Integration Test Plan | https://openvisa.atlassian.net/wiki/spaces/DD/pages/84082689/DIS+QA+Test+Plan
8 | Rebuild Plan | https://openvisa.atlassian.net/wiki/spaces/DD/pages/117702657/DIS+IaC+Validation+263+-+Deloitte+Clarifications+and+Required+Deliverables | Fairoze's answer attached at the bottom of the page. | [8 empty] | Fairoze's answer attached at the bottom of the page.
9 | Updated API Spec | https://openvisa.atlassian.net/wiki/spaces/DD/pages/122224641/Updated+API+Integration+Data+APIs+Specification | [9 empty] | [SCRUM-17] OpenAPI 3.0 Spec for DIS API — Deloitte to produce, Open Visa to review - Jira Please note that the earlier API specifications were discussed and approved during SCRUM 17. The new API specs have now been considered for this sprint,
10 | Staging & Prod | https://openvisa.atlassian.net/wiki/spaces/DD/pages/111771652/DIS+-+Open+Visa+GCP+Staging+Production+Infra+Plan
2. Last Week Deliverables
11 | Last Week Deliverables | Code modification for Ingestion- update table names |  |  | Preety | Completed |  | 8th June |  |  | GREEN | Updated and deployment to start from 11th June
12 | Last Week Deliverables | Code modification for Doc processing- update table names |  |  | Satyarth | Completed |  | 8th June |  |  | GREEN | Updated and deployment to start from 11th June
13 | Last Week Deliverables | Code modification for External checks- update table names |  |  | Neeraj | Completed |  | 8th June |  |  | GREEN | Updated and deployment to start from 11th June
14 | Last Week Deliverables | Code modification for Drools- update table names |  |  | Preety | Completed |  | 5th June |  |  | GREEN | Updated and deployment to start from 11th June
15 | Last Week Deliverables | Code modification for OPA- update table names |  |  | Vidhyotha | Completed |  | 8th June |  |  | GREEN | Updated and deployment to start from 11th June
16 | Last Week Deliverables | Code addition for Recommendation- update data in callback_events table |  |  | Satyarth/Ranita | Completed |  | 9th June |  |  | GREEN | Updated and deployment to start from 11th June
17 | Last Week Deliverables | Code modification for Recommendation- update table names |  |  | Satyarth | Completed |  | 9th June |  |  | GREEN | Updated and deployment to start from 11th June
18 | Last Week Deliverables | Code modification – Impersonation (Ingestion,Doc processing, External checks ,OPA,Recommendation) . To be implemented post the DB connection issue was resolved on 3rd June |  |  | Preety, Satyarth, Vidhyotha, Neeraj | Completed |  | 10th-12th June |  |  | GREEN | Code base has been updated, with impersonation. To be deployed from tomorrow
19 | Last Week Deliverables | Ingestion – with updated unit test cases |  |  | Vinay | Completed |  | 8th June |  |  | GREEN | Completed
20 | Last Week Deliverables | Doc processing – with updated unit test cases |  |  | Vinay | Completed |  | 8th June |  |  | GREEN | Completed
21 | Last Week Deliverables | External checks – with updated unit test cases |  |  | Maaz | Completed |  | 8th June |  |  | GREEN | Completed
22 | Last Week Deliverables | Drools – with updated unit test cases |  |  | Aarush | Completed |  | 5th June |  |  | GREEN | Completed
23 | Last Week Deliverables | OPA– with updated unit test cases |  |  | Aarush | Completed |  | Already done. |  |  | GREEN | Completed
24 | Last Week Deliverables | Recommendation – with updated unit test cases |  |  | Maaz | Completed |  | 9th June |  |  | GREEN | Completed
25 | Last Week Deliverables | Final changes in the response in the dis-end-api status |  |  | Neeraj | Completed |  | 10th June |  |  | GREEN | Updated and deployed
26 | Last Week Deliverables | KMS Keys Mapping |  |  | DevOps | Completed |  | 11th June |  |  | GREEN | Completed
27 | Last Week Deliverables | Pub/Sub Trigger |  |  | DevOps+ App | Completed |  | 11th June |  |  | GREEN | Completed
28 | Last Week Deliverables | Redeployment of modules(Ingestion, Doc proc, external checks,Drools,OPA, Recommendation) |  |  | DevOps+ App | Completed |  | 11th-15th June |  |  | GREEN | All modules are redeployed
3. This Sprint Integration Testing
29 | This Sprint Integration Testing | Doc Processing — Integration Testing | 1. Design and implement integration testing framework with reusable mock fixtures for external dependencies 2. Develop end-to-end integration tests for document ingestion and processing workflows 3. Add validation for multiple document scenarios including custom, unsupported, and negative cases 4. Validate downstream failures across messaging, DB, and analytics systems 5. Configure CI/CD execution and documentation |  | Aarush | In-progress | 18th June 2026 | 22nd June 2026 |  | Changes of DLP have been made by Satyarth but it has not been checked as the deployment from DevOps end is blocked. | RED | 1. Integration Test Suited is created and Pushed in OV Env (qa/vinrai/doc-processing-integration-testing-suite) 2. Test Execution is in Progress in OV Env
30 | This Sprint Integration Testing | Doc Processing — Code Fixes and Enhancements | Code will be enhanced, tested, pushed, and deployed |  | Satyarth | In-progress | 18th June 2026 | 22nd June 2026 |  |  | YELLOW
31 | This Sprint Integration Testing | External Checks — Integration Testing | 1. Implement integration tests for external provider workflows 2. Add API tests with mock provider services 3. Validate live provider integrations (auth, request/response, latency, availability) 4. Validate DB persistence and audit logs 5. Validate GCP services (Pub/Sub, Secret Manager) 6. Test retry, failures, and exceptions 7. Integrate tests with CI/CD pipelines |  | Maaz | In-progress | 18th June 2026 | 22nd June 2026 | 1. Source code and configuration variable updates are pending completion from developer, with integration testing to follow to validate the implemented bug fixes. |  | YELLOW | 1. Integration Test Suited is created and Pushed in OV Env (qa/maaz/integration-testing) 2. Test Execution is in Progress in OV Env
32 | This Sprint Integration Testing | External Checks — Code Fixes and Enhancements | Code will be enhanced, tested, pushed, and deployed |  | Neeraj | In-progress | 18th June 2026 | 22nd June 2026 |  |  | YELLOW
33 | This Sprint Integration Testing | Recommendation — Integration Testing | 1. Build mock-based integration testing framework for dependencies 2. Develop end-to-end tests for orchestration and recommendation flows 3. Add negative scenarios for failures and invalid inputs 4. Configure CI/CD quality gates and automation workflows 5. Prepare reporting and execution documentation |  | Maaz | Completed | 18th June 2026 | 19th June 2026 | 1. Require application entries for Positive, Negative and Edge Case Scenario from Satyarth/Preety |  | YELLOW
34 | This Sprint Integration Testing | Recommendation — Code Fixes and Enhancements | Code will be enhanced, tested, pushed, and deployed |  | Ranita / Satyarth | Completed | 18th June 2026 | 19th June 2026 |  |  | YELLOW
35 | This Sprint Integration Testing | Ingestion — Integration Testing | 1. Design and implement end-to-end integration testing framework 2. Develop full-chain coverage for external provider workflows and dispatcher validation 3. Add positive and negative scenarios for reliability 4. Configure CI/CD automation for execution 5. Prepare documentation and execution guidelines |  | Vinay | Completed | 15th June 2026 | 18th June 2026 |  |  | YELLOW
36 | This Sprint Integration Testing | Ingestion — Code Fixes and Enhancements | Code will be enhanced, tested, pushed, and deployed |  | Preety / Satyarth | Completed | 15th June 2026 | 18th June 2026 |  |  | YELLOW
37 | This Sprint Integration Testing | OPA — Integration Testing | 1. Build integration testing framework using live OPA server and rego execution 2. Validate policy decisions across rule packages via HTTP 3. Add test cases for valid/invalid inputs and missing attributes 4. Validate data-driven rules using JSON reference data 5. Configure CI/CD execution and documentation |  | Aarush | Completed | 18th June 2026 | 19th June 2026 |  |  | YELLOW
38 | This Sprint Integration Testing | OPA — Code Fixes and Enhancements | Code will be enhanced, tested, pushed, and deployed |  | Vidhyotha | Completed | 19th June 2026 | 22nd June 2026 |  |  | YELLOW
39 | This Sprint Integration Testing | Drools — Integration Testing | 1. Build integration testing framework using Spring Boot and DRL rules 2. Develop end-to-end tests for rule evaluation (hard/soft rules) 3. Add positive/negative and edge-case scenarios 4. Validate rule execution sequence and state updates 5. Configure CI/CD execution and documentation |  | Aarush | In-progress | 19th June 2026 | 23nd June 2026 | Working on building the integration test suite | 1. Need to check the feasibiltiy of Proposed Cloudbuild Trigger to solve Cloud SQL connection issue | RED | Integration Test Suite is created, finalization and Execution of Integration Test suite is pending in OV Env
40 | This Sprint Integration Testing | Drools — Code Fixes and Enhancements | Code will be enhanced, tested, pushed, and deployed |  | Preety | In-progress | 19th June 2026 | 24th June 2026 |  |  | RED
41 | This Sprint Integration Testing | Integration — E2E Testing | 1. Finalize E2E scenarios across all modules 2. Validate environment readiness (Dev & Staging) 3. Execute full happy-path flows 4. Execute negative/failure scenarios 5. Validate data consistency and traceability 6. Capture execution reports and sign-off summary |  | Vinay & Maaz | In-progress | 23rd June 2026 | 29th June 2026 |  |  | YELLOW
42 | This Sprint Integration Testing | Regression — E2E Testing | 1. Finalize regression test suite 2. Validate no impact from recent changes 3. Execute regression scenarios (positive/negative/boundary) 4. Re-run impacted integration/E2E flows 5. Retest defects and ensure stability 6. Prepare regression report and QA sign-off |  | Vinay & Aarush | In-progress | 23rd June 2026 | 29th June 2026 |  |  | YELLOW
43 | This Sprint Integration Testing | Performance — E2E Testing | 1. Define performance scope and workload model 2. Validate performance environment readiness 3. Execute load and baseline testing 4. Measure KPIs (latency, throughput, error rate, etc.) 5. Execute stress/spike/soak tests 6. Analyze bottlenecks and prepare final report |  | Vinay, Aarush & Maaz | In-progress | 23rd June 2026 | 29th June 2026 |  |  | YELLOW
44 | This Sprint Integration Testing | Final Stabilization — Code Fixes & Drift Resolution |  |  | Testing Team | In-progress | 29th June 2026 | 30th June 2026 |  |  | YELLOW | Buffer for stabilization/backlog fixes before final sign-off
4. This Sprint Rebuild Plan
45 | This Sprint Rebuild Plan | Prerequisites :1 — Service Account |  |  | Chris | Planned | 19th June 2026 | 19th June 2026 | WIF setup is dependant on this |  | YELLOW | Execution: Manual Destroyable via IaC: No
46 | This Sprint Rebuild Plan | Prerequisites : 2 — Whitelisting : Cloud Build Connects with the Github Repo |  |  | Prateek/Chris | Planned | 19th June 2026 | 19th June 2026 | Individual Implementor should have Cloud Build Admin Access, Github Repo Admin Accesss |  | YELLOW | Execution: Manual Destroyable via IaC: No
47 | This Sprint Rebuild Plan | Prerequisites : 3 — Create an Bucket for storing the statefile |  |  | Chris | Planned | 19th June 2026 | 19th June 2026 |  |  | YELLOW | Execution: Manual Destroyable via IaC: No
48 | This Sprint Rebuild Plan | Prerequisites : 4 — GCP Project Host VPC VPC Subnets Assigning Permissions : Compute Network Admin, Compute Network User & Compute Security Admin on BootStrap Service Accounts, Cloud Identity service agents |  |  | Chris | Planned | 19th June 2026 | 19th June 2026 |  |  | YELLOW | Execution: Manual/CICD
49 | This Sprint Rebuild Plan | AFTER HALF A DAY OF REVIEWING THE PRE REQUISITES THE FOLLOWING CAN BE STARTED |  |  |  | Gate / Note |  |  |  |  | GREEN | Section marker / sequencing note
50 | This Sprint Rebuild Plan | WIF Setup : 1 — Github/CI/CloudBuild.yaml |  |  | Prateek | Planned | 22nd June 2026 | 22nd June 2026 | Prerequisites : 3 | This will be done through Cloud Build, triggered by dis-infra-wif | YELLOW | Execution: CI/CD Destroyable via IaC: No
51 | This Sprint Rebuild Plan | WIF Setup : 2 — Repository Usage |  |  | Chris | Planned | 22nd June 2026 | 22nd June 2026 |  | This will be done through Cloud Build, triggered by dis-infra-wif | YELLOW | Execution: Destroyable via IaC: No
52 | This Sprint Rebuild Plan | WIF Setup : 3 — Update .tfvars |  |  | Prateek | Planned | 22nd June 2026 | 22nd June 2026 | WIF Pool | This will be done through Cloud Build, triggered by dis-infra-wif | YELLOW | Execution: Destroyable via IaC: No
53 | This Sprint Rebuild Plan | Infrastructure : 1 — KMS |  |  | Prateek | Planned | 23rd June 2026 | 25th June 2026 | SA |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: No
54 | This Sprint Rebuild Plan | Infrastructure : 2 — Service Accounts |  |  | Prateek | Planned | 23rd June 2026 | 24th June 2026 |  |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: Yes, except foundation SAs
55 | This Sprint Rebuild Plan | Infrastructure : 3 — IAM |  |  | Chris (Only for Host Project) | Planned | 23rd June 2026 | 24th June 2026 | SA, GCS, Pub/Sub |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: Yes, except bootstrap/foundation IAM
56 | This Sprint Rebuild Plan | Infrastructure : 4 — PSA |  |  | Prateek | Planned | 23rd June 2026 | 24th June 2026 |  |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: No
57 | This Sprint Rebuild Plan | Infrastructure : 5 — Serverless VPC Connector |  |  | Prateek | Planned | 23rd June 2026 | 24th June 2026 |  |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: No routine destroy
58 | This Sprint Rebuild Plan | Infrastructure : 6 — Cloud SQL |  |  | Prateek | Planned | 23rd June 2026 | 24th June 2026 | KMS, Secret Manager, PSA |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: No by default
59 | This Sprint Rebuild Plan | Infrastructure : 7 — Artifact Registry |  |  | Prateek | Planned | 23rd June 2026 | 24th June 2026 | KMS |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: Yes, with impact
60 | This Sprint Rebuild Plan | Infrastructure : 8 — BigQuery |  |  | Prateek | Planned | 23rd June 2026 | 24th June 2026 | KMS |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: Yes, with data loss
61 | This Sprint Rebuild Plan | Infrastructure : 9 — Cloud Run |  |  | Prateek | Planned | 23rd June 2026 | 24th June 2026 | Artifact Registry, SA, Serverless VPC, Cloud SQL, BigQuery, Pub/Sub, GCS, Secret Manager |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: No from infra pipeline
62 | This Sprint Rebuild Plan | Infrastructure : 10 — DLP |  |  | Prateek | Planned | 23rd June 2026 | 24th June 2026 |  |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: Yes
63 | This Sprint Rebuild Plan | Infrastructure : 11 — Document AI Processors |  |  | Prateek | Planned | 23rd June 2026 | 24th June 2026 |  | Doc processors will need to be deployed as cloud run, source code modifications have been done. It's not compatible in OV env yet. | RED | Execution: dis-infrastructure Destroyable via IaC: No
64 | This Sprint Rebuild Plan | Infrastructure : 12 — Host Firewall Rule |  |  | Prateek | Planned | 23rd June 2026 | 24th June 2026 |  |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: Yes
65 | This Sprint Rebuild Plan | Infrastructure : 13 — GCS |  |  | Prateek | Planned | 23rd June 2026 | 24th June 2026 | Various |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: Partially
66 | This Sprint Rebuild Plan | Infrastructure : 14 — Pub/Sub Topics |  |  | Prateek | Planned | 23rd June 2026 | 24th June 2026 | KMS |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: No by default
67 | This Sprint Rebuild Plan | Infrastructure : 15 — Secret Manager |  |  | Prateek | Planned | 23rd June 2026 | 24th June 2026 | KMS |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: No
68 | This Sprint Rebuild Plan | Infrastructure : 16 — Billing Budgets |  |  | Prateek | Planned | 23rd June 2026 | 24th June 2026 |  |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: Yes
69 | This Sprint Rebuild Plan | Infrastructure : 17 — API Gateway |  |  | Prateek | Planned | 23rd June 2026 | 24th June 2026 | Service account |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: Yes
70 | This Sprint Rebuild Plan | DB Setup : 1 — Postgres Privileges |  |  | Ranita/Prateek | Planned | 25th June 2026 | 25th June 2026 | Cloud SQL, database user SA | This will be done through Cloud Build, triggered by dis-data-layer | YELLOW | Execution: dis-data-layer Destroyable via IaC: Yes
71 | This Sprint Rebuild Plan | DB Setup : 2 — Cloud SQL Tables |  |  | Ranita/Prateek | Planned | 25th June 2026 | 25th June 2026 | Cloud SQL, database user SA, privileges | This will be done through Cloud Build, triggered by dis-data-layer | YELLOW | Execution: dis-data-layer Destroyable via IaC: No
72 | This Sprint Rebuild Plan | Deployment : 1 — Deployment of Cloud Run Services |  |  | App Team/Prateek | Planned | 26th June 2026 | 29th June 2026 |  | Each cloud run service has to be deployed by running CI pipelines from all the different repos | YELLOW | Execution: Deployment
73 | This Sprint Rebuild Plan | Deployment : 2 — Cloud Functions |  |  | App Team/Prateek | Planned | 26th June 2026 | 29th June 2026 |  | Cloud functions will be deployed directly through CI pipeline | YELLOW | Execution: Deployment
74 | This Sprint Rebuild Plan | Deployment : 3 — Pub/Sub Subscriptions |  |  | Prateek | Planned | 30th June 2026 | 30th June 2026 | Topics, Cloud Run, SA |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: No by default
75 | This Sprint Rebuild Plan | Deployment : 4 — Eventarc Triggers |  |  | Prateek | Planned | 30th June 2026 | 30th June 2026 | Pub/Sub, Cloud Run, GCS, Eventarc SA |  | GREEN | Execution: dis-infrastructure Destroyable via IaC: Yes
76 | This Sprint Rebuild Plan | Validation and Testing |  |  | Prateek | Planned | 1st July 2026 | 1st July 2026 |  |  | GREEN | Execution:
77 | This Sprint Rebuild Plan | Buffer for Troubleshooting |  |  | Prateek | Planned | 2nd July 2026 | 2nd July 2026 |  |  | GREEN | Execution:
5. Next Sprint Updated API Spec
78 | Next Sprint Updated API Spec | Application list / review queue | Endpoint: GET /api/v1/applications/status?startDateTime={startDate}&endDateTime={endDate} Headers: { Authorization: Bearer , X-Source-Channel: visakey } Request: { startDate: "10-06-2026", endDate: "10-06-2026" } Response: { dis_application_id, visa_type, status, completeness_score, callback_url, outcome, total_processing_time_ms } PG Tables: ['applications', 'recommendations'] |  | Neeraj | In-progress | 17th June 2026 | 18th June 2026 | Code is ready. Migration Pending to OV Env |  | YELLOW | Estimated timeline: 16 hours
79 | Next Sprint Updated API Spec | Application detail / recommendation | Endpoint: GET /api/v1/app_decision/{id}/details Headers: { Authorization: Bearer , X-Source-Channel: visakey, X-Request-ID: <application_id> } Request: { dis_application_id } Response: { dis_Application_id, outcome, recommendation_at, component_scores, soft_flag_rules, callback_url, status } PG Tables: ['recommendations', 'callback_events'] |  | Neeraj | In-progress | 18th June 2026 | 19th June 2026 | Code is ready. Migration Pending to OV Env |  | YELLOW | Estimated timeline: 16 hours
80 | Next Sprint Updated API Spec | Glass Box decision trail (Drools + OPA results) | Endpoint: GET /api/v1/rules_evaluations/{id}/details Headers: { Authorization: Bearer , X-Source-Channel: visakey, X-Request-ID: <application_id> } Request: { dis_application_id } Response: { dis_application_id, drool_evaluation: { rule_id, rule_name, rule_category, outcome, severity, reasoning, rule_version_id, evaluated_at }, opa_evaluation: { policy_name, policy_type, outcome, denial_reasons } } PG Tables: ['drools_evaluations', 'opa_evaluations'] |  | Neeraj | In-progress | 18th June 2026 | 19th June 2026 | Code is ready. Migration Pending to OV Env |  | YELLOW | Estimated timeline: 8 hours
81 | Next Sprint Updated API Spec | Documents + extractions | Endpoint: GET /api/v1/doc_processing/{id}/details Headers: { Authorization: Bearer , X-Source-Channel: visakey, X-Request-ID: <application_id> } Request: { dis_application_id } Response: { dis_application_id, document_type, requirement_tier, processing_tier, criticality, processing_status, quality_score, dlp_classifications, normalized_fields, fraud_score, fraud_status, confidence_score } PG Tables: ['documents', 'document_extractions'] |  | Neeraj | In-progress | 19th June 2026 | 22nd June 2026 | Code is ready. Migration Pending to OV Env |  | YELLOW | Estimated timeline: 8 hours
82 | Next Sprint Updated API Spec | External checks | Endpoint: GET /api/v1/external_checks/{id}/details Headers: { Authorization: Bearer , X-Source-Channel: visakey, X-Request-ID: <application_id> } Request: { dis_application_id } Response: { dis_application_id, check_type, request_payload, response_payload, check_Status, risk_level, confidence_score, created_at } PG Tables: ['external_checks'] |  | Neeraj | In-progress | 22nd June 2026 | 23rd June 2026 | Code is ready. Migration Pending to OV Env |  | YELLOW | Estimated timeline: 8 hours
83 | Next Sprint Updated API Spec | Testing + Deployment | Endpoint: All Modules Headers: - Request: - Response: - PG Tables: - |  | Testing Team | Planned after Integration Testing | 1st July 2026 | 3rd July 2026 |  |  | YELLOW | Estimated timeline: 16 hours
6. Next Sprint Staging & Prod
84 | Next Sprint Staging & Prod | 1 — Terraform Setup | • Create tfvars for dev, staging and production to externalize environment-specific values. • Parameterize project IDs so app/data/shared service project references are not hardcoded. • Parameterize network variables including VPC, subnet, connector, NAT and regional configuration inputs. • Separate Terraform modules to improve reuse, maintainability and environment promotion consistency. |  | Terraform | Planned | 1st July 2026 | 3rd July 2026 | Existing Terraform baseline and confirmed dev/staging/prod project and network inputs. As per the LLD, the network for staging and dev is same(Non prod), is it still going be same or we need a different vpc for stagginhg |  | GREEN | Task Description: Refactor and prepare Terraform configuration so the same codebase can support dev, staging and production deployments through environment-specific inputs and reusable modules. Deliverables: Environment tfvars files, parameterized Terraform variables, reusable module structure and updated Terraform execution layout. Estimated Hours: 64
85 | Next Sprint Staging & Prod | 2 — Staging IAM | • Create staging deployer service account for pipeline/Terraform deployment activities. • Create staging runtime service account for Cloud Run workload execution. • Apply required IAM roles using least-privilege permissions for staging deployment and runtime operations. • Configure Workload Identity Federation for staging CI/CD authentication without long-lived service account keys. |  | Terraform, DevOps | Planned | 2nd July 2026 | 6th July 2026 | Terraform Setup; staging project IDs; confirmed IAM role matrix; CI/CD identity provider details. Are we using separate SA for staging and prod? Deployment should be same or different? Are we using any AD(Active directory)? |  | RED | Task Description: Implement staging identity and access management required for deployment automation, runtime execution and secure federation-based access. Deliverables: Staging deployer SA, staging runtime SA, IAM bindings and staging WIF configuration. Estimated Hours: 48
86 | Next Sprint Staging & Prod | 3 — Staging Network | • Attach staging workload/projects to the non-prod VPC or Shared VPC as applicable. • Create serverless VPC connector for staging Cloud Run private connectivity. • Configure NAT for controlled outbound connectivity from staging workloads. |  | Network | Planned | 2nd July 2026 | 6th July 2026 | Terraform Setup; confirmed non-prod VPC/subnet details; network permissions and routing requirements. |  | RED | Task Description: Connect the staging environment to the non-production network foundation and configure required private connectivity and egress controls. Deliverables: Staging VPC attachment, VPC connector and NAT configuration validated for staging workloads. Estimated Hours: 32
87 | Next Sprint Staging & Prod | 4 — Staging App | • Deploy Cloud Run service for staging using the configured runtime service account and environment settings. • Set up staging load balancer with backend integration for Cloud Run. • Attach Cloud Armor policy to protect the staging external entry point. |  | App, Network, Security | Planned | 7th July 2026 | 13th July 2026 | Staging IAM; Staging Network; application image/artifact availability; approved ingress and security configuration. |  | YELLOW | Task Description: Deploy the application into staging and expose it through the approved ingress path with load balancing and edge protection. Deliverables: Staging Cloud Run service, load balancer configuration and Cloud Armor attachment. Estimated Hours: 40
88 | Next Sprint Staging & Prod | 5 — Staging CI/CD | • Add staging deploy stage to the CI/CD pipeline. • Add approval gate for staging deployment where required. • Test staging deployment flow end-to-end including authentication, deployment execution and basic rollback readiness. |  | DevOps | Planned | 1st July 2026 | 3rd July 2026 | Terraform Setup; Staging IAM/WIF; application artifact publishing; pipeline repository access. |  | YELLOW | Task Description: Update the deployment pipeline to support automated staging deployment with approvals and deployment validation. Deliverables: Updated staging deployment pipeline, approval gate and successful staging deployment test evidence. Estimated Hours: 40
90 | Next Sprint Staging & Prod | 6 — Production IAM | • Create production deployer service account for approved production deployment activities. • Create production runtime service account for Cloud Run workload execution. • Apply production IAM roles using least-privilege permissions and separation from non-production access. • Configure Workload Identity Federation for production CI/CD authentication without long-lived service account keys. |  | Terraform, DevOps | Planned | 14th July 2026 | 15th July 2026 | Terraform Setup; production project IDs; approved production IAM role matrix; CI/CD identity provider details. Are we using any AD(Active directory)? |  | RED | Task Description: Implement production identity and access management with strict access boundaries for deployment automation, runtime execution and federated authentication. Deliverables: Production deployer SA, production runtime SA, IAM bindings and production WIF configuration. Estimated Hours: 48 We will be dealing with the end-user data.
91 | Next Sprint Staging & Prod | 7 — Production Network | • Attach production workload/projects to the production VPC or Shared VPC as applicable. • Create serverless VPC connector for production Cloud Run private connectivity. • Configure NAT for controlled outbound connectivity from production workloads. |  | Network | Planned | 14th July 2026 | 16th July 2026 | Terraform Setup; confirmed production VPC/subnet details; production network permissions and routing requirements. |  | RED | Task Description: Connect the production environment to the production network foundation and configure required private connectivity and controlled egress. Deliverables: Production VPC attachment, VPC connector and NAT configuration validated for production workloads. Estimated Hours: 32 We will be dealing with the end-user data.
92 | Next Sprint Staging & Prod | 8 — Production App | • Deploy Cloud Run service for production using the configured runtime service account and production settings. • Set up production load balancer with backend integration for Cloud Run. • Attach Cloud Armor policy to protect the production external entry point. |  | App, Network, Security | Planned | 17th July 2026 | 24th July 2026 | Production IAM; Production Network; approved production artifact/image; production DNS/certificate or ingress prerequisites. |  | RED | Task Description: Deploy the application into production and expose it through the approved production ingress path with load balancing and Cloud Armor protection. Deliverables: Production Cloud Run service, production load balancer configuration and Cloud Armor attachment. Estimated Hours: 40 We will be dealing with the end-user data.
93 | Next Sprint Staging & Prod | 9 — Production CI/CD | • Add production promote stage to move approved build artifacts into production. • Add production approval gate for controlled release execution. • Test production deployment flow including promotion, deployment execution and validation checks. |  | DevOps | Planned | 14th July 2026 | 14th July 2026 | Staging CI/CD; Production IAM/WIF; approved production release process; production deployment approvals. |  | RED | Task Description: Update the CI/CD process to support controlled promotion into production with approval gates and deployment validation. Deliverables: Production promotion stage, approval gate and successful production deployment test evidence. Estimated Hours: 40 We will be dealing with the end-user data.

## Risks
Open Red and Yellow Risk Summary
Scope: Items from the Unified WBS where Risk Level is RED or YELLOW.
Total open RED risks: 10
Total open YELLOW risks: 26
Completed RED/YELLOW items excluded: 6
Open Risk Count by Workstream
Source / Workstream | RED | YELLOW
Next Sprint Staging & Prod | 6 | 2
Next Sprint Updated API Spec | 0 | 6
This Sprint Integration Testing | 3 | 7
This Sprint Rebuild Plan | 1 | 11
Detailed Open RED / YELLOW Risk Register
# | Source / Workstream | Work Item | Sub-Task | Owner | Status | Start Date | Target / End Date | Dependencies | Blockers / Risk | Risk Level | Deloitte Comment | OV Comment | Details / Action Required
29 | This Sprint Integration Testing | Doc Processing — Integration Testing | 1. Design and implement integration testing framework with reusable mock fixtures for external dependencies 2. Develop end-to-end integration tests for document ingestion and processing workflows 3. Add validation for multiple document scenarios including custom, unsupported, and negative cases 4. Validate downstream failures across messaging, DB, and analytics systems 5. Configure CI/CD execution and documentation | Aarush | In-progress | 18th June 2026 | 22nd June 2026 |  | Changes of DLP have been made by Satyarth but it has not been checked as the deployment from DevOps end is blocked. | RED | 1. Integration Test Suited is created and Pushed in OV Env (qa/vinrai/doc-processing-integration-testing-suite) 2. Test Execution is in Progress in OV Env |  | Risk/Blocker: Changes of DLP have been made by Satyarth but it has not been checked as the deployment from DevOps end is blocked. Deloitte note: 1. Integration Test Suited is created and Pushed in OV Env (qa/vinrai/doc-processing-integration-testing-suite) 2. Test Execution is in Progress in OV Env
30 | This Sprint Integration Testing | Doc Processing — Code Fixes and Enhancements | Code will be enhanced, tested, pushed, and deployed | Satyarth | In-progress | 18th June 2026 | 22nd June 2026 |  |  | YELLOW |  |  | No additional detail captured in source WBS.
31 | This Sprint Integration Testing | External Checks — Integration Testing | 1. Implement integration tests for external provider workflows 2. Add API tests with mock provider services 3. Validate live provider integrations (auth, request/response, latency, availability) 4. Validate DB persistence and audit logs 5. Validate GCP services (Pub/Sub, Secret Manager) 6. Test retry, failures, and exceptions 7. Integrate tests with CI/CD pipelines | Maaz | In-progress | 18th June 2026 | 22nd June 2026 | 1. Source code and configuration variable updates are pending completion from developer, with integration testing to follow to validate the implemented bug fixes. |  | YELLOW | 1. Integration Test Suited is created and Pushed in OV Env (qa/maaz/integration-testing) 2. Test Execution is in Progress in OV Env |  | Dependency: 1. Source code and configuration variable updates are pending completion from developer, with integration testing to follow to validate the implemented bug fixes. Deloitte note: 1. Integration Test Suited is created and Pushed in OV Env (qa/maaz/integration-testing) 2. Test Execution is in Progress in OV Env
32 | This Sprint Integration Testing | External Checks — Code Fixes and Enhancements | Code will be enhanced, tested, pushed, and deployed | Neeraj | In-progress | 18th June 2026 | 22nd June 2026 |  |  | YELLOW |  |  | No additional detail captured in source WBS.
39 | This Sprint Integration Testing | Drools — Integration Testing | 1. Build integration testing framework using Spring Boot and DRL rules 2. Develop end-to-end tests for rule evaluation (hard/soft rules) 3. Add positive/negative and edge-case scenarios 4. Validate rule execution sequence and state updates 5. Configure CI/CD execution and documentation | Aarush | In-progress | 19th June 2026 | 23nd June 2026 | Working on building the integration test suite | 1. Need to check the feasibiltiy of Proposed Cloudbuild Trigger to solve Cloud SQL connection issue | RED | Integration Test Suite is created, finalization and Execution of Integration Test suite is pending in OV Env |  | Dependency: Working on building the integration test suite Risk/Blocker: 1. Need to check the feasibiltiy of Proposed Cloudbuild Trigger to solve Cloud SQL connection issue Deloitte note: Integration Test Suite is created, finalization and Execution of Integration Test suite is pending in OV Env
40 | This Sprint Integration Testing | Drools — Code Fixes and Enhancements | Code will be enhanced, tested, pushed, and deployed | Preety | In-progress | 19th June 2026 | 24th June 2026 |  |  | RED |  |  | No additional detail captured in source WBS.
41 | This Sprint Integration Testing | Integration — E2E Testing | 1. Finalize E2E scenarios across all modules 2. Validate environment readiness (Dev & Staging) 3. Execute full happy-path flows 4. Execute negative/failure scenarios 5. Validate data consistency and traceability 6. Capture execution reports and sign-off summary | Vinay & Maaz | In-progress | 23rd June 2026 | 29th June 2026 |  |  | YELLOW |  |  | No additional detail captured in source WBS.
42 | This Sprint Integration Testing | Regression — E2E Testing | 1. Finalize regression test suite 2. Validate no impact from recent changes 3. Execute regression scenarios (positive/negative/boundary) 4. Re-run impacted integration/E2E flows 5. Retest defects and ensure stability 6. Prepare regression report and QA sign-off | Vinay & Aarush | In-progress | 23rd June 2026 | 29th June 2026 |  |  | YELLOW |  |  | No additional detail captured in source WBS.
43 | This Sprint Integration Testing | Performance — E2E Testing | 1. Define performance scope and workload model 2. Validate performance environment readiness 3. Execute load and baseline testing 4. Measure KPIs (latency, throughput, error rate, etc.) 5. Execute stress/spike/soak tests 6. Analyze bottlenecks and prepare final report | Vinay, Aarush & Maaz | In-progress | 23rd June 2026 | 29th June 2026 |  |  | YELLOW |  |  | No additional detail captured in source WBS.
44 | This Sprint Integration Testing | Final Stabilization — Code Fixes & Drift Resolution |  | Testing Team | In-progress | 29th June 2026 | 30th June 2026 |  |  | YELLOW | Buffer for stabilization/backlog fixes before final sign-off |  | Deloitte note: Buffer for stabilization/backlog fixes before final sign-off
45 | This Sprint Rebuild Plan | Prerequisites :1 — Service Account |  | Chris | Planned | 19th June 2026 | 19th June 2026 | WIF setup is dependant on this |  | YELLOW | Execution: Manual Destroyable via IaC: No |  | Dependency: WIF setup is dependant on this Deloitte note: Execution: Manual Destroyable via IaC: No
46 | This Sprint Rebuild Plan | Prerequisites : 2 — Whitelisting : Cloud Build Connects with the Github Repo |  | Prateek/Chris | Planned | 19th June 2026 | 19th June 2026 | Individual Implementor should have Cloud Build Admin Access, Github Repo Admin Accesss |  | YELLOW | Execution: Manual Destroyable via IaC: No |  | Dependency: Individual Implementor should have Cloud Build Admin Access, Github Repo Admin Accesss Deloitte note: Execution: Manual Destroyable via IaC: No
47 | This Sprint Rebuild Plan | Prerequisites : 3 — Create an Bucket for storing the statefile |  | Chris | Planned | 19th June 2026 | 19th June 2026 |  |  | YELLOW | Execution: Manual Destroyable via IaC: No |  | Deloitte note: Execution: Manual Destroyable via IaC: No
48 | This Sprint Rebuild Plan | Prerequisites : 4 — GCP Project Host VPC VPC Subnets Assigning Permissions : Compute Network Admin, Compute Network User & Compute Security Admin on BootStrap Service Accounts, Cloud Identity service agents |  | Chris | Planned | 19th June 2026 | 19th June 2026 |  |  | YELLOW | Execution: Manual/CICD |  | Deloitte note: Execution: Manual/CICD
50 | This Sprint Rebuild Plan | WIF Setup : 1 — Github/CI/CloudBuild.yaml |  | Prateek | Planned | 22nd June 2026 | 22nd June 2026 | Prerequisites : 3 | This will be done through Cloud Build, triggered by dis-infra-wif | YELLOW | Execution: CI/CD Destroyable via IaC: No |  | Dependency: Prerequisites : 3 Risk/Blocker: This will be done through Cloud Build, triggered by dis-infra-wif Deloitte note: Execution: CI/CD Destroyable via IaC: No
51 | This Sprint Rebuild Plan | WIF Setup : 2 — Repository Usage |  | Chris | Planned | 22nd June 2026 | 22nd June 2026 |  | This will be done through Cloud Build, triggered by dis-infra-wif | YELLOW | Execution: Destroyable via IaC: No |  | Risk/Blocker: This will be done through Cloud Build, triggered by dis-infra-wif Deloitte note: Execution: Destroyable via IaC: No
52 | This Sprint Rebuild Plan | WIF Setup : 3 — Update .tfvars |  | Prateek | Planned | 22nd June 2026 | 22nd June 2026 | WIF Pool | This will be done through Cloud Build, triggered by dis-infra-wif | YELLOW | Execution: Destroyable via IaC: No |  | Dependency: WIF Pool Risk/Blocker: This will be done through Cloud Build, triggered by dis-infra-wif Deloitte note: Execution: Destroyable via IaC: No
63 | This Sprint Rebuild Plan | Infrastructure : 11 — Document AI Processors |  | Prateek | Planned | 23rd June 2026 | 24th June 2026 |  | Doc processors will need to be deployed as cloud run, source code modifications have been done. It's not compatible in OV env yet. | RED | Execution: dis-infrastructure Destroyable via IaC: No |  | Risk/Blocker: Doc processors will need to be deployed as cloud run, source code modifications have been done. It's not compatible in OV env yet. Deloitte note: Execution: dis-infrastructure Destroyable via IaC: No
70 | This Sprint Rebuild Plan | DB Setup : 1 — Postgres Privileges |  | Ranita/Prateek | Planned | 25th June 2026 | 25th June 2026 | Cloud SQL, database user SA | This will be done through Cloud Build, triggered by dis-data-layer | YELLOW | Execution: dis-data-layer Destroyable via IaC: Yes |  | Dependency: Cloud SQL, database user SA Risk/Blocker: This will be done through Cloud Build, triggered by dis-data-layer Deloitte note: Execution: dis-data-layer Destroyable via IaC: Yes
71 | This Sprint Rebuild Plan | DB Setup : 2 — Cloud SQL Tables |  | Ranita/Prateek | Planned | 25th June 2026 | 25th June 2026 | Cloud SQL, database user SA, privileges | This will be done through Cloud Build, triggered by dis-data-layer | YELLOW | Execution: dis-data-layer Destroyable via IaC: No |  | Dependency: Cloud SQL, database user SA, privileges Risk/Blocker: This will be done through Cloud Build, triggered by dis-data-layer Deloitte note: Execution: dis-data-layer Destroyable via IaC: No
72 | This Sprint Rebuild Plan | Deployment : 1 — Deployment of Cloud Run Services |  | App Team/Prateek | Planned | 26th June 2026 | 29th June 2026 |  | Each cloud run service has to be deployed by running CI pipelines from all the different repos | YELLOW | Execution: Deployment |  | Risk/Blocker: Each cloud run service has to be deployed by running CI pipelines from all the different repos Deloitte note: Execution: Deployment
73 | This Sprint Rebuild Plan | Deployment : 2 — Cloud Functions |  | App Team/Prateek | Planned | 26th June 2026 | 29th June 2026 |  | Cloud functions will be deployed directly through CI pipeline | YELLOW | Execution: Deployment |  | Risk/Blocker: Cloud functions will be deployed directly through CI pipeline Deloitte note: Execution: Deployment
78 | Next Sprint Updated API Spec | Application list / review queue | Endpoint: GET /api/v1/applications/status?startDateTime={startDate}&endDateTime={endDate} Headers: { Authorization: Bearer , X-Source-Channel: visakey } Request: { startDate: "10-06-2026", endDate: "10-06-2026" } Response: { dis_application_id, visa_type, status, completeness_score, callback_url, outcome, total_processing_time_ms } PG Tables: ['applications', 'recommendations'] | Neeraj | In-progress | 17th June 2026 | 18th June 2026 | Code is ready. Migration Pending to OV Env |  | YELLOW | Estimated timeline: 16 hours |  | Dependency: Code is ready. Migration Pending to OV Env Deloitte note: Estimated timeline: 16 hours
79 | Next Sprint Updated API Spec | Application detail / recommendation | Endpoint: GET /api/v1/app_decision/{id}/details Headers: { Authorization: Bearer , X-Source-Channel: visakey, X-Request-ID: <application_id> } Request: { dis_application_id } Response: { dis_Application_id, outcome, recommendation_at, component_scores, soft_flag_rules, callback_url, status } PG Tables: ['recommendations', 'callback_events'] | Neeraj | In-progress | 18th June 2026 | 19th June 2026 | Code is ready. Migration Pending to OV Env |  | YELLOW | Estimated timeline: 16 hours |  | Dependency: Code is ready. Migration Pending to OV Env Deloitte note: Estimated timeline: 16 hours
80 | Next Sprint Updated API Spec | Glass Box decision trail (Drools + OPA results) | Endpoint: GET /api/v1/rules_evaluations/{id}/details Headers: { Authorization: Bearer , X-Source-Channel: visakey, X-Request-ID: <application_id> } Request: { dis_application_id } Response: { dis_application_id, drool_evaluation: { rule_id, rule_name, rule_category, outcome, severity, reasoning, rule_version_id, evaluated_at }, opa_evaluation: { policy_name, policy_type, outcome, denial_reasons } } PG Tables: ['drools_evaluations', 'opa_evaluations'] | Neeraj | In-progress | 18th June 2026 | 19th June 2026 | Code is ready. Migration Pending to OV Env |  | YELLOW | Estimated timeline: 8 hours |  | Dependency: Code is ready. Migration Pending to OV Env Deloitte note: Estimated timeline: 8 hours
81 | Next Sprint Updated API Spec | Documents + extractions | Endpoint: GET /api/v1/doc_processing/{id}/details Headers: { Authorization: Bearer , X-Source-Channel: visakey, X-Request-ID: <application_id> } Request: { dis_application_id } Response: { dis_application_id, document_type, requirement_tier, processing_tier, criticality, processing_status, quality_score, dlp_classifications, normalized_fields, fraud_score, fraud_status, confidence_score } PG Tables: ['documents', 'document_extractions'] | Neeraj | In-progress | 19th June 2026 | 22nd June 2026 | Code is ready. Migration Pending to OV Env |  | YELLOW | Estimated timeline: 8 hours |  | Dependency: Code is ready. Migration Pending to OV Env Deloitte note: Estimated timeline: 8 hours
82 | Next Sprint Updated API Spec | External checks | Endpoint: GET /api/v1/external_checks/{id}/details Headers: { Authorization: Bearer , X-Source-Channel: visakey, X-Request-ID: <application_id> } Request: { dis_application_id } Response: { dis_application_id, check_type, request_payload, response_payload, check_Status, risk_level, confidence_score, created_at } PG Tables: ['external_checks'] | Neeraj | In-progress | 22nd June 2026 | 23rd June 2026 | Code is ready. Migration Pending to OV Env |  | YELLOW | Estimated timeline: 8 hours |  | Dependency: Code is ready. Migration Pending to OV Env Deloitte note: Estimated timeline: 8 hours
83 | Next Sprint Updated API Spec | Testing + Deployment | Endpoint: All Modules Headers: - Request: - Response: - PG Tables: - | Testing Team | Planned after Integration Testing | 1st July 2026 | 3rd July 2026 |  |  | YELLOW | Estimated timeline: 16 hours |  | Deloitte note: Estimated timeline: 16 hours
85 | Next Sprint Staging & Prod | 2 — Staging IAM | • Create staging deployer service account for pipeline/Terraform deployment activities. • Create staging runtime service account for Cloud Run workload execution. • Apply required IAM roles using least-privilege permissions for staging deployment and runtime operations. • Configure Workload Identity Federation for staging CI/CD authentication without long-lived service account keys. | Terraform, DevOps | Planned | 2nd July 2026 | 6th July 2026 | Terraform Setup; staging project IDs; confirmed IAM role matrix; CI/CD identity provider details. Are we using separate SA for staging and prod? Deployment should be same or different? Are we using any AD(Active directory)? |  | RED | Task Description: Implement staging identity and access management required for deployment automation, runtime execution and secure federation-based access. Deliverables: Staging deployer SA, staging runtime SA, IAM bindings and staging WIF configuration. Estimated Hours: 48 |  | Dependency: Terraform Setup; staging project IDs; confirmed IAM role matrix; CI/CD identity provider details. Are we using separate SA for staging and prod? Deployment should be same or different? Are we using any AD(Active directory)? Deloitte note: Task Description: Implement staging identity and access management required for deployment automation, runtime execution and secure federation-based access. Deliverables: Staging deployer SA, staging runtime SA, IAM bindings and staging WIF configuration. Estimated Hours: 48
86 | Next Sprint Staging & Prod | 3 — Staging Network | • Attach staging workload/projects to the non-prod VPC or Shared VPC as applicable. • Create serverless VPC connector for staging Cloud Run private connectivity. • Configure NAT for controlled outbound connectivity from staging workloads. | Network | Planned | 2nd July 2026 | 6th July 2026 | Terraform Setup; confirmed non-prod VPC/subnet details; network permissions and routing requirements. |  | RED | Task Description: Connect the staging environment to the non-production network foundation and configure required private connectivity and egress controls. Deliverables: Staging VPC attachment, VPC connector and NAT configuration validated for staging workloads. Estimated Hours: 32 |  | Dependency: Terraform Setup; confirmed non-prod VPC/subnet details; network permissions and routing requirements. Deloitte note: Task Description: Connect the staging environment to the non-production network foundation and configure required private connectivity and egress controls. Deliverables: Staging VPC attachment, VPC connector and NAT configuration validated for staging workloads. Estimated Hours: 32
87 | Next Sprint Staging & Prod | 4 — Staging App | • Deploy Cloud Run service for staging using the configured runtime service account and environment settings. • Set up staging load balancer with backend integration for Cloud Run. • Attach Cloud Armor policy to protect the staging external entry point. | App, Network, Security | Planned | 7th July 2026 | 13th July 2026 | Staging IAM; Staging Network; application image/artifact availability; approved ingress and security configuration. |  | YELLOW | Task Description: Deploy the application into staging and expose it through the approved ingress path with load balancing and edge protection. Deliverables: Staging Cloud Run service, load balancer configuration and Cloud Armor attachment. Estimated Hours: 40 |  | Dependency: Staging IAM; Staging Network; application image/artifact availability; approved ingress and security configuration. Deloitte note: Task Description: Deploy the application into staging and expose it through the approved ingress path with load balancing and edge protection. Deliverables: Staging Cloud Run service, load balancer configuration and Cloud Armor attachment. Estimated Hours: 40
88 | Next Sprint Staging & Prod | 5 — Staging CI/CD | • Add staging deploy stage to the CI/CD pipeline. • Add approval gate for staging deployment where required. • Test staging deployment flow end-to-end including authentication, deployment execution and basic rollback readiness. | DevOps | Planned | 1st July 2026 | 3rd July 2026 | Terraform Setup; Staging IAM/WIF; application artifact publishing; pipeline repository access. |  | YELLOW | Task Description: Update the deployment pipeline to support automated staging deployment with approvals and deployment validation. Deliverables: Updated staging deployment pipeline, approval gate and successful staging deployment test evidence. Estimated Hours: 40 |  | Dependency: Terraform Setup; Staging IAM/WIF; application artifact publishing; pipeline repository access. Deloitte note: Task Description: Update the deployment pipeline to support automated staging deployment with approvals and deployment validation. Deliverables: Updated staging deployment pipeline, approval gate and successful staging deployment test evidence. Estimated Hours: 40
90 | Next Sprint Staging & Prod | 6 — Production IAM | • Create production deployer service account for approved production deployment activities. • Create production runtime service account for Cloud Run workload execution. • Apply production IAM roles using least-privilege permissions and separation from non-production access. • Configure Workload Identity Federation for production CI/CD authentication without long-lived service account keys. | Terraform, DevOps | Planned | 14th July 2026 | 15th July 2026 | Terraform Setup; production project IDs; approved production IAM role matrix; CI/CD identity provider details. Are we using any AD(Active directory)? |  | RED | Task Description: Implement production identity and access management with strict access boundaries for deployment automation, runtime execution and federated authentication. Deliverables: Production deployer SA, production runtime SA, IAM bindings and production WIF configuration. Estimated Hours: 48 We will be dealing with the end-user data. |  | Dependency: Terraform Setup; production project IDs; approved production IAM role matrix; CI/CD identity provider details. Are we using any AD(Active directory)? Deloitte note: Task Description: Implement production identity and access management with strict access boundaries for deployment automation, runtime execution and federated authentication. Deliverables: Production deployer SA, production runtime SA, IAM bindings and production WIF configuration. Estimated Hours: 48 We will be dealing with the end-user data.
91 | Next Sprint Staging & Prod | 7 — Production Network | • Attach production workload/projects to the production VPC or Shared VPC as applicable. • Create serverless VPC connector for production Cloud Run private connectivity. • Configure NAT for controlled outbound connectivity from production workloads. | Network | Planned | 14th July 2026 | 16th July 2026 | Terraform Setup; confirmed production VPC/subnet details; production network permissions and routing requirements. |  | RED | Task Description: Connect the production environment to the production network foundation and configure required private connectivity and controlled egress. Deliverables: Production VPC attachment, VPC connector and NAT configuration validated for production workloads. Estimated Hours: 32 We will be dealing with the end-user data. |  | Dependency: Terraform Setup; confirmed production VPC/subnet details; production network permissions and routing requirements. Deloitte note: Task Description: Connect the production environment to the production network foundation and configure required private connectivity and controlled egress. Deliverables: Production VPC attachment, VPC connector and NAT configuration validated for production workloads. Estimated Hours: 32 We will be dealing with the end-user data.
92 | Next Sprint Staging & Prod | 8 — Production App | • Deploy Cloud Run service for production using the configured runtime service account and production settings. • Set up production load balancer with backend integration for Cloud Run. • Attach Cloud Armor policy to protect the production external entry point. | App, Network, Security | Planned | 17th July 2026 | 24th July 2026 | Production IAM; Production Network; approved production artifact/image; production DNS/certificate or ingress prerequisites. |  | RED | Task Description: Deploy the application into production and expose it through the approved production ingress path with load balancing and Cloud Armor protection. Deliverables: Production Cloud Run service, production load balancer configuration and Cloud Armor attachment. Estimated Hours: 40 We will be dealing with the end-user data. |  | Dependency: Production IAM; Production Network; approved production artifact/image; production DNS/certificate or ingress prerequisites. Deloitte note: Task Description: Deploy the application into production and expose it through the approved production ingress path with load balancing and Cloud Armor protection. Deliverables: Production Cloud Run service, production load balancer configuration and Cloud Armor attachment. Estimated Hours: 40 We will be dealing with the end-user data.
93 | Next Sprint Staging & Prod | 9 — Production CI/CD | • Add production promote stage to move approved build artifacts into production. • Add production approval gate for controlled release execution. • Test production deployment flow including promotion, deployment execution and validation checks. | DevOps | Planned | 14th July 2026 | 14th July 2026 | Staging CI/CD; Production IAM/WIF; approved production release process; production deployment approvals. |  | RED | Task Description: Update the CI/CD process to support controlled promotion into production with approval gates and deployment validation. Deliverables: Production promotion stage, approval gate and successful production deployment test evidence. Estimated Hours: 40 We will be dealing with the end-user data. |  | Dependency: Staging CI/CD; Production IAM/WIF; approved production release process; production deployment approvals. Deloitte note: Task Description: Update the CI/CD process to support controlled promotion into production with approval gates and deployment validation. Deliverables: Production promotion stage, approval gate and successful production deployment test evidence. Estimated Hours: 40 We will be dealing with the end-user data.